## Sheet1
| THÁNG 7 |  |  | THÁNG 8
| 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Pre-Production | Cả nhóm
Resource 2D | Phạm Nguyễn Thành Long-Lê Đình An | bar: THÁNG 8 1 to THÁNG 8 3
Resource 3D | Phạm Nguyễn Thành Long | bar: THÁNG 8 1 to THÁNG 8 3
Engine Structure | Phạm Quang Huy - Nguyễn Thành Tâm | bar: THÁNG 8 1 to THÁNG 8 3
Physic |  |  | Trương Minh Vũ - Nguyễn Thành Tâm | bar: THÁNG 8 1 to THÁNG 8 12
Âm thanh |  |  |  | THÁNG 8 10: Phạm Quang Huy
Animation |  |  |  | THÁNG 8 1: Trương Minh Vũ
Hiển thị UI |  |  |  | THÁNG 8 7: Phạm Quang Huy - Nguyễn Thành Tâm
Port Android |  |  |  | THÁNG 8 7: Phạm Quang Huy - Nguyễn Thành Tâm
GamePlay |  |  |  | THÁNG 8 9: Nguyễn Thành Tâm-Trương Minh Vũ - Phạm Quang Huy
Water Coustic |  |  |  | THÁNG 8 27: Phạm Quang Huy
Tối Ưu và Sửa Lỗi |  |  |  | THÁNG 8 23: Nguyễn Thành Tâm - Phạm Quang Huy
Chuẩn bị cho buổi thuyết trình về kết quả trong giai đoạn production |  |  |  | THÁNG 8 30: Cả nhóm
Thuyết trình

## Compatibility Report
Compatibility Report for KeHoachCongViec.xls
Run on 7/17/2013 22:28
The following features in this workbook are not supported by earlier versions of Excel. These features may be lost or degraded when opening this workbook in an earlier version of Excel or if you save this workbook in an earlier file format.
Minor loss of fidelity | # of occurrences | Version
Some cells or styles in this workbook contain formatting that is not supported by the selected file format. These formats will be converted to the closest format available. | 5 | Excel 97-2003